## 20-2-26
Daily Progress Report
PROJECT NAME: | [9 empty] | Date:
Prepared By: | [9 empty] | Weather Conditons
Approved By: | [9 empty] | Temperature
Sr. No | Floor | Activity Name | Activity Type | UOM | Total Quantity | Achieved Quantity (Till previous day) | Acheieved Quantity (Till Today) | Activity % as of previous day | Activity % As of Today | Forecast Completion Date | Variance % | Comments/ Constraints
1 |  | Column Steel Fixing | CIV | No. | 10 | 8 | 9 | 80% | 90% |  | 10%
2 |  | Column Formwork Fixing | CIV | No. | [6 empty] | 0%
3 |  | Block Masonry | GW | M² | [6 empty] | 0%
4 |  | Slab Concreting | CIV | M³ | [6 empty] | 0%
5 |  | Indoor Units Installation | HVAC | No. | [6 empty] | 0%
6 |  | Duct Installation (Fresh Air & Exhaust) | HVAC | M² | 100 | 65 | 70 | 65% | 70% |  | 5%
7 |  | Copper Pipe Installation | HVAC | LM | [6 empty] | 0%
8 |  | PPR Pipe Installation | PL | LM | [6 empty] | 0%
9 | [10 empty] | 0%
10 | [10 empty] | 0%
11 | [10 empty] | 0%
Sr. No | Direct Staff |  | Attendance |  | Sr.No | Labour Force Category |  |  | Attendance |  | Comments/ Constraints
1 | Project Manager |  |  |  | 1 | Steel Fixer
2 | Construction Manager |  |  |  | 2 | General Labor
3 | Site Supervisor |  |  |  | 3 | Carpenter
4 | MEP Engineer |  |  |  | 4 | Ceiling Worker
5 | MEP Technician |  |  |  | 5 | Plumber
6 | Site Engineer |  |  |  | 6 | Carpenter
7 | Storekeeper |  |  |  | 7 | Plumber
Sr. No | Equipment Deployed |  | Status |  | PROJECT MANAGER's COMMENTS
1
2
3
4

## Data Bank
Activity Data Bank | UOM | CODE |  | Weather | Project | Labor Force | Site Staff | STATUS
Column Steel Fixing | M² | CIV | Civil | Sunny | RAW BANK Polygone | Steel Fixer | Project Manager | Rental
Column Formwork Fixing | Ton | ELE | Electrical | Cloudy | Shamsar | Carpenter | Construction Manager | Parkland
Column Concrete | No. | HVAC | HVAC Works | Rainy | PET Clinic | General Labor | Site Engineer
Shear Wall Steel Fixing | M³ | PL | Plumbing |  | Angel Cosmetics | Tiler | Site Supervisor
Block Masonry | LM | FF | Firefighting |  | RAWSUR | Ceiling Worker | Site Forman
Internal Plaster |  | FIN | Finishing |  |  | Plumber | MEP Engineer
Screed |  | GW | Grey Works |  |  | HVAC Technician | MEP Technician
Shear Wall Formwork | [5 empty] | Wood Worker | Storekeeper
Shear Wall Concrete | [5 empty] | Painter
Slab Formwork
Slab Reinforcement
Slab Concrete
PPR Pipe Installation
PVC/UPVC Drainage Pipe Installation
HDPE Pipe Installation
FF Pipe Installation
Duct Installation (Supply & Return)
Duct Installation (Fresh & Exhaust)
Copper Pipe Installation
Duct Insulation
Copper Pipe Insulation
OVAL Duct/Circular Duct
Ventilation Fans
Indoor Units Installation
Floor & Wall Conduiting
Cable Tray
CDR Pipe
Façade Frame
Façade Glass
Ceiling Framing
Ceiling Installation
Wall & Floor Tiling
Doors
Paint
External Plaster